## project
e-SENS WP5.2 eHealth Domain Pilot Plan (2015-01-14)
[6 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
|  |  |  | PLAN | PLAN | 2014-12-01 |  |  |  |  | 2015-01-01 |  |  |  | 2015-02-01 |  |  |  | 2015-03-01 |  |  |  | 2015-04-01 |  |  |  |  | 2015-05-01 |  |  |  | 2015-06-01 |  |  |  | 2015-07-01 |  |  |  |  | 2015-08-01 |  |  |  | 2015-09-01 |  |  |  |  | 2015-10-01 |  |  |  | 2015-11-01 |  |  |  | 2015-12-01 |  |  |  |  | 2016-01-01 |  |  |  | 2016-02-01 |  |  |  | 2016-03-01
Phase | Task ID | ACTIVITY | DESCRIPTION | START | DURATION | Weeks |  |  | Holidays | [51 empty] | holidays
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
1 - Baselining | 1.1 | Understand e-SENS Pilot Scope and Plan | Get in touch with the rationale behind the e-SENS WP5.2 eHealth pilot Plan for eHealth, namely concerning; structure, timings, and activities; and confirm Member State ability to commit to the plan proposed. The plan MUST clear communicate the expected outcomes so that all stakeholders may manage expectations from the beginning. | 1 | 9
| 1.2 | Study epSOS Req. and Spec., and update them (in EXPAND) accordingly to e-SENS | Understand the Patient Summary and ePrescription (eDispensation) use cases, namely the complete workflows and the implications introduced by the adoption of the e-SENS Building Blocks (having as baseline the epSOS specifications). | 1 | 9
| 1.3 | Evaluate whether OpenNCP and Central Services can be reused | Deep analyse and describe the impact of the incorporation of each e-SENS proposed Building Block or BB feature is such a way that we can move from architectural perspective to implementation level with clear specifications for MS or Communities to implement. With this input in hand a unbiased analysis can be made in order to understand the level of reusability possible with epSOS NCP reference implementation and central services | 1 | 9
2 - Non-Repudiation | 2.1 | Restart epSOS Central Services (migration activities should be considered) | In order to assure the epSOS architecture all needed conditions to work, the first step is find the needed conditions to restart the current central services. This step will allow MS to technically restart exchange of data by allowing the automatic synchronization of infrastructural communications settings. | 10 | 8
| 2.2 | NCP BSP (27002:2005) alignment with ISO 27002:2013 |  | 10 | 8
| 2.3 | Requirements and recommendations list update and alignment with the updated legislature (eIDAS, Patients’ Rights, Cross-Border HC, Guidelines on PS & eP, etc.) |  | 10 | 8
| 2.4 | Adding e-SENS: Non-repudiation BB feature (into OpenNCP) |  | 10 | 4
| 2.5 | OpenNCP QA and Release |  | 14 | 2
| 2.6 | MS instantiate OpenNCP (update or fresh install) | Member states instantiate the National Contact Point based on the OpenNCP reference implementation, provided by epSOS and the OpenNCP Community (currently steered by EXPAND) | 16 | 3
| 2.7 | MS Pre-Connectathon Testing | The testing step aims at gathering strong evidenced of compliance with specifications and profiles (if possible, collected face to face by independent entity) from the several Member States piloting in e-SENS. | 19 | 2
| 2.8 | MS Connectathon Testing |  | 21 | 1
| 2.9 | Sustainably Fix Connectathon issues |  | 22 | 2
| 2.10 | OpenNCP QA and Release |  | 24 | 1
| 2.11 | MS update local instalattion of NCP |  | 25 | 1
| 2.12 | MS perform Regression Testing | The Audit step aims at gathering, from each MS willing to pilot, a readiness report on the several dimensions of the pilot (technical, semantic, security, organizational and legal – if applicable) | 26 | 1
| 2.13 | PILOTING - Stage 1 | This step identifies the moment where 2 (two) or more MS reach a readiness level where the minimal conditions have been achieved for exchanging clinical data. The current plan proposes an agile way to “Start Piloting” namely by suggesting that pilots may start before all the e-SENS Building Blocks of BB feature are in place. The proposed agile way, points to a plan where MS could re-start the epSOS PPT environments without any changes to the epSOS implementation. From then on, any improvement could be built on top of that working infrastructure and services. | 27 | 20
3 - TrustEstab + ConfigServices | 3.1 | Understanding new BB specification and implementation impact |  | 16 | 4
| 3.2 | Adding e-SENS: Trust Establishment (into CS) |  | 18 | 4
| 3.3 | Adding e-SENS: Configuration Services (into CS) |  | 25 | 4
| 3.4 | Refactor OpenNCP according to the new CS Architecture and Operation paradigm | Evolve the epSOS Central Services rationale (architecture and services) by adopting e-SENS Building Blocks or BB features. This step will have impact also at NCP level where refactoring will need to be made in order to allow the improved articulation model between NCPs. | 29 | 4
| 3.5 | TEST new CS infrastructure |  | 32 | 2
| 3.6 | Deploy new CS infrastructure |  | 34 | 2
| 3.7 | Integration TESTING with OpenNCP |  | 36 | 2
| 3.8 | OpenNCP QA and Release |  | 38 | 2
| 3.9 | MS update operation model according to new paradigm of CS |  | 40 | 2
| 3.10 | MS update local installation of NCP |  | 42 | 2
| 3.11 | MS perform Regression Testing |  | 44 | 2
| 3.12 | PILOTING - Stage 2 |  | 46 | 15
4 - Patient eID | 4.1 | Understanding new BB specification and implementation impact |  | 40 | 4
| 4.2 | Adding e-SENS: eID (into NCP) |  | 42 | 6
| 4.3 | Integration TESTING centrally |  | 48 | 2
| 4.4 | OpenNCP QA and Release |  | 50 | 1
| 4.5 | MS adopt infrastructure for eID |  | 45 | 4
| 4.6 | MS deploy national infrastructure for eID |  | 49 | 4
| 4.7 | MS update local installation of NCP |  | 53 | 1
| 4.8 | MS perform Integration Test: NCP+eID |  | 54 | 1
| 4.9 | MS perform Regression Testing |  | 55 | 1
| 4.10 | PILOTING - Stage 3 |  | 58 | 8