## general_report
OpenNCP Workbench
Displaying 129 issues at 02/Mar/16 6:54 PM.
Issue Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due Date
Bug | AA-28 | [ PPT ] Identification Service Audit Messages do not contain the Mapping Service Active Participant | Marcelo Fonseca | Marcelo Fonseca | Critical | Reopened | Unresolved | 21/Dec/12 9:34 AM | 2013-03-21 23:23
Epic | AA-31 | Extended Security Safegards | Konstantin Hyppönen | Licínio kustra Mano | Major | Open | Unresolved | 2013-01-30 23:40 | 24/Feb/16 4:32 PM
Improvement | AA-32 | Update Audit Manager with epSOS 2.0 audit trail EventIDs | Massimiliano Masi | Konstantin Hyppönen | Major | Open | Unresolved | 15/Feb/13 1:33 PM | 16/Jun/15 3:40 PM
Epic | AM-1 | Update Audit Manager for epSOS 2 messages compliance | Marcelo Fonseca | Licínio kustra Mano | Critical | Open | Unresolved | 15/Jul/13 9:54 AM | 15/Jul/13 10:33 AM
Bug | AM-21 | [PAT] Audit Message for "Issuance of HCP Identity Assertion" operation uses wrong IHE code | Marcelo Fonseca | Marcelo Fonseca | Major | Reopened | Unresolved | 08/Apr/14 10:23 AM | 24/Feb/16 4:39 PM
Bug | CDT-14 | CDA displaying wrong effectiveTime | Kostas Karkaletsis | João Cunha | Major | In Progress | Unresolved | 06/Jul/15 5:00 PM | 08/Jul/15 7:16 PM
Improvement | CM-1 | Implement consent revocation | Heiko Zimmermann | Stéphane Spahni | Critical | Open | Unresolved | 2013-03-22 13:58 | 16/Jun/15 10:50 AM
Improvement | COMA-11 | Configuration Manager now caches the values and all components need to be restarted on config variable values changed | Kostas Karkaletsis | Kostas Karkaletsis | Major | Open | Unresolved | 29/Apr/15 1:01 PM | 22/Feb/16 4:07 PM
Improvement | COMA-12 | Improve Configuration Manager Scalability | Kostas Karkaletsis | Jerome Subiger | Major | Open | Unresolved | 24/Feb/16 6:12 PM | 24/Feb/16 6:12 PM
New Feature | COMA-8 | [ Config. Manager ] IT Policy do not allow passwords to be stored in database | Stéphane Spahni | Marcelo Fonseca | Major | Open | Unresolved | 13/Dec/12 1:16 PM | 24/Feb/16 4:35 PM
Sub-task | COMA-9 | COMA-8 Clarify with Italy the strategy to adopt for passwords in property files / database | Stefan Gustafsson | Stefan Gustafsson | Major | Reopened | Unresolved | 2013-01-03 11:06 | 01/Aug/13 3:14 PM
Improvement | EADC-11 | Implement NEW test cases for eADC | Marcelo Fonseca | Licínio kustra Mano | Minor | Open | Unresolved | 2013-01-16 10:35 | 02/Apr/13 9:13 AM
Bug | EADC-23 | The records created in the eADC database contain only outbound transactions and lack of information | Marko Peric | Kostas Karkaletsis | Major | Open | Unresolved | 2014-03-20 13:41 | 16/Jun/15 12:01 PM
Task | EADC-6 | [IMPEDED-nextSprint] Describe the sufficient test cases needed to safely verify the functionality of the eADC component | Marcelo Fonseca | Steen Manniche | Minor | Open | Unresolved | 2013-01-09 10:50 | 02/Apr/13 9:14 AM
Improvement | EID-3 | provide addin version in info page for each addin | Alexandre Santos | Soeren Bittins | Trivial | To Do | Unresolved | 04/Dec/15 4:18 PM | 04/Dec/15 4:21 PM
Improvement | EID-4 | repackage PDF processing components | Soeren Bittins | Alexandre Santos | Minor | To Do | Unresolved | 04/Dec/15 4:19 PM | 25/Feb/16 5:07 PM
Task | EID-5 | change informational picture of Italian CNS in eID client | Marcello Melgara | Soeren Bittins | Trivial | To Do | Unresolved | 04/Dec/15 4:20 PM | 04/Dec/15 4:21 PM
Improvement | EID-6 | Error in EXPAND CP for eID | Massimiliano Masi | João Cunha | Major | To Do | Unresolved | 23/Feb/16 12:09 PM | 25/Feb/16 5:06 PM
Bug | EPW-10 | Error handling CDA documents | Gareth Woodham | Anders Nyström | Major | Reopened | Unresolved | 04/Feb/13 12:30 PM | 2013-09-09 11:12
Improvement | EPW-39 | Populate "pharmacy name" field in XDR submit message | Stefan Gustafsson | Gareth Woodham | Major | Open | Unresolved | 30/Apr/13 2:52 PM | 17/Dec/13 12:53 PM
Bug | EPW-46 | getStringIgnoreSettings warning | Gareth Woodham | Konstantin Hyppönen | Major | Open | Unresolved | 14/May/13 2:34 PM | 15/May/13 9:38 AM
Task | EPW-51 | Develop a user interface for filling the HCER document (epsos-web) | Stefan Gustafsson | Konstantin Hyppönen | Major | Open | Unresolved | 12/Feb/13 5:46 PM | 04/Jun/13 11:06 AM
Task | EPW-52 | Web service call from epsos-web to NCP-B client connector for submitting the HCER | Stefan Gustafsson | Konstantin Hyppönen | Major | Open | Unresolved | 12/Feb/13 5:54 PM | 04/Jun/13 11:10 AM
Task | EPW-53 | Constructor for valid HCER CDA documents according to the guidelines formulated in PT-186 (epsos-web) | Stefan Gustafsson | Konstantin Hyppönen | Major | Open | Unresolved | 12/Feb/13 5:51 PM | 04/Jun/13 11:10 AM
Improvement | EPW-64 | update wicket version | Anders Nyström | Anders Nyström | Major | Open | Unresolved | 06/Aug/13 11:43 AM | 2013-09-09 11:22
Bug | EPW-70 | Surname prefix is shown in wrong position | Konstantin Hyppönen | Konstantin Hyppönen | Major | Reopened | Unresolved | 2013-09-11 14:13 | 2013-09-12 13:38
Bug | EPW-71 | Units in eDispensation documents are not always in UCUM | Konstantin Hyppönen | Konstantin Hyppönen | Major | Open | Unresolved | 2013-09-24 21:02 | 2013-10-01 14:10
Bug | EPW-77 | Wrong date displayed for blood pressure | Gareth Woodham | Stéphane Spahni | Major | Open | Unresolved | 2013-11-14 10:14 | 2013-11-14 10:15
Bug | EPW-80 | Change of product name must be possible even if substitution is prohibited | Anders Nyström | Konstantin Hyppönen | Major | Open | Unresolved | 06/Feb/14 1:31 PM | 06/Feb/14 1:31 PM
Bug | EPW-85 | Epsos-Web does not find PS anymore if OpenNCP is 2.1.* | Gareth Woodham | Stéphane Spahni | Critical | Open | Unresolved | 2014-11-21 14:35 | 2014-11-21 14:35
Bug | GPB-10 | After sending a consent Portal returns an INFO message | Kostas Karkaletsis | Gergely Héja | Minor | Reopened | Unresolved | 17/Apr/13 12:10 PM | 2013-09-03 13:31
Bug | GPB-23 | Mixed languages in patient summary documents | Kostas Karkaletsis | Gergely Héja | Major | Open | Unresolved | 2013-10-03 12:11 | 05/Feb/15 11:00 AM
Bug | GPB-24 | Unable to fill in Problem form of HCER | Kostas Karkaletsis | Gergely Héja | Major | Open | Unresolved | 2013-10-04 16:52 | 16/Jun/15 3:32 PM
Story | GPB-28 | XDM: export media the Patient Summary CDA | Licínio kustra Mano | Licínio kustra Mano | Major | Open | Unresolved | 2013-10-16 02:52 | 30/Apr/14 1:39 PM
Bug | GPB-29 | Language files not available | Kostas Karkaletsis | Gergely Héja | Critical | Reopened | Unresolved | 2013-11-07 09:56 | 16/Jun/15 10:51 AM
Improvement | GPB-31 | [PAT] HCP Assurance Audit Messages are being written in NCP-B side in Validation Tool | Marcelo Fonseca | Marcelo Fonseca | Major | Open | Unresolved | 07/Apr/14 4:45 PM | 16/Apr/14 2:35 PM
New Feature | GPB-57 | Allow user to select the country of origin in Patient Access portlet in case of stork authentication in different country | Kostas Karkaletsis | Kostas Karkaletsis | Major | Open | Unresolved | 27/Apr/15 9:47 PM | 27/Apr/15 9:47 PM
Story | GPB-60 | SMP-SML Specification for eHealth | Licínio kustra Mano | Rui Alves | Major | Open | Unresolved | 15/Jun/15 3:40 PM | 24/Feb/16 4:58 PM
Improvement | GPB-67 | Implement eID LAM+ | Alexandre Santos | Alexandre Santos | Major | Open | Unresolved | 2015-11-24 17:00 | 2015-11-24 17:00 | 2015-11-27
Bug | GPB-68 | XSPA role "medical doctor" has not been specified | Kostas Karkaletsis | João Cunha | Minor | Open | Unresolved | 2016-01-21 16:33 | 24/Feb/16 11:12 AM
Bug | GPB-69 | Prevent CRRF | Jerome Subiger | Jerome Subiger | Major | Open | Unresolved | 24/Feb/16 5:42 PM | 24/Feb/16 5:43 PM
Improvement | GPB-70 | Enforce account lockout after several failed login | Jerome Subiger | Jerome Subiger | Major | Open | Unresolved | 24/Feb/16 5:42 PM | 24/Feb/16 5:44 PM
Bug | GPB-71 | Block body parameters | Jerome Subiger | Jerome Subiger | Major | Open | Unresolved | 24/Feb/16 5:45 PM | 24/Feb/16 5:50 PM
Bug | GPB-72 | Remove business and security logic from the client side. | Jerome Subiger | Jerome Subiger | Major | Open | Unresolved | 24/Feb/16 5:47 PM | 25/Feb/16 4:53 PM
Improvement | GPB-73 | Set the AllowScriptAccess | Jerome Subiger | Jerome Subiger | Major | Open | Unresolved | 24/Feb/16 5:58 PM | 24/Feb/16 5:58 PM
Improvement | GPB-74 | Verify that parameter values are in their expected ranges and types. Do not output debugging error messages and exceptions | Jerome Subiger | Jerome Subiger | Major | Open | Unresolved | 24/Feb/16 5:59 PM | 24/Feb/16 5:59 PM
Epic | INT-21 | Actual Sprint Goal | Licínio kustra Mano | Licínio kustra Mano | Blocker | Open | Unresolved | 2013-01-02 09:44 | 2013-09-05 14:55 | 2013-01-17
Epic | INT-24 | Optional features or improvements | Steen Manniche | Licínio kustra Mano | Major | Open | Unresolved | 2013-01-09 11:21 | 24/Feb/16 4:35 PM
Epic | INT-36 | OpenNCP CTS2 compliance for Terminologies Sync | Steen Manniche | Licínio kustra Mano | Major | Open | Unresolved | 2013-01-30 23:41 | 2013-10-11 10:37
Epic | INT-37 | Support Issues | Steen Manniche | Licínio kustra Mano | Major | Open | Unresolved | 2013-01-30 23:49 | 24/Feb/16 4:34 PM
Bug | OP-18 | Access control to OpenATNA logviewer | Mika Myllyvirta | Konstantin Hyppönen | Major | Open | Unresolved | 03/Dec/13 2:25 PM | 03/Dec/13 2:25 PM
Bug | OP-20 | Missing JAR required for OpenATNA | Kostas Karkaletsis | João Cunha | Major | Open | Unresolved | 17/Jun/15 6:44 PM | 25/Feb/16 6:31 PM
Improvement | OPENNCP-24 | Duplicate configuration of keystore and truststore properties | Konstantin Hyppönen | Konstantin Hyppönen | Major | Reopened | Unresolved | 2013-01-24 20:18 | 24/Feb/16 4:34 PM
Epic | OPENNCP-32 | OpenNCP Continuous Integration Environment Optimizations | Licínio kustra Mano | Marcelo Fonseca | Major | Open | Unresolved | 2013-10-11 10:23 | 2013-11-25 19:30
Bug | OPENNCP-47 | Jenkins build failure - Report links not available | Marcelo Fonseca | Marcelo Fonseca | Major | In Progress | Unresolved | 2014-01-27 09:30 | 2014-01-27 09:36
Task | OPENNCP-57 | Fwd: Contact Info > OpenHIE - National Pregnancy Registry here in South Africa | Licínio kustra Mano | Licínio kustra Mano | Major | Open | Unresolved | 2014-03-18 09:46 | 16/Jun/15 12:06 PM
Improvement | OPENNCP-59 | [PAT] Implement compliance with epSOS 2 Specs for XCPD, XCA, XDR transactions | Heiko Zimmermann | Marcelo Fonseca | Critical | Open | Unresolved | 08/Apr/14 4:43 PM | 26/Feb/16 10:31 AM
Improvement | OPENNCP-60 | [PAT] Invoke EADC, Audit Manager and XCPD Validator in an asynchronous mode in order to have better performance | Heiko Zimmermann | Kostas Karkaletsis | Critical | Open | Unresolved | 08/Apr/14 4:43 PM | 26/Feb/16 10:32 AM
Task | OPENNCP-67 | Confirm if the trillium code branch is correctly defined and being used and that the Master and Development branch have not being wrongly used. | Kostas Karkaletsis | Licínio kustra Mano | Major | In Progress | Unresolved | 2014-09-22 15:04 | 16/Jun/15 11:59 AM
Bug | OPENNCP-68 | TRC-STS 1.0.1 has wrong commons-lang jar version | Licínio kustra Mano | Stéphane Spahni | Major | Open | Unresolved | 2014-11-21 14:27 | 2014-11-21 14:27 | 2014-11-21
Task | OPENNCP-73 | Installation of OpenNCP into WebLogic (EC) | Jerome Subiger | Licínio kustra Mano | Minor | Open | Unresolved | 15/Jun/15 2:00 PM | 29/Jun/15 4:15 PM
New Feature | OPENNCP-74 | Migration To Weblogic | Jerome Subiger | Jerome Subiger | Critical | Open | Unresolved | 15/Jun/15 3:14 PM | 24/Feb/16 3:01 PM
Bug | OPENNCP-81 | Direct Brokered Trust - Identity Provider (STS) for issuance of IdA | Licínio kustra Mano | Rui Alves | Major | Open | Unresolved | 2015-09-10 19:11 | 25/Feb/16 2:23 PM
Epic | OPENNCP-83 | Security and performance improvements | Jerome Subiger | Jerome Subiger | Major | Open | Unresolved | 22/Feb/16 4:04 PM | 24/Feb/16 7:28 PM | 2016-03-31
Epic | OPENNCP-85 | Integration with SMP/SML | Jerome Subiger | Jerome Subiger | Major | Open | Unresolved | 24/Feb/16 4:52 PM | 24/Feb/16 5:02 PM
Task | OPENNCP-86 | Run load test session. | Jerome Subiger | Jerome Subiger | Critical | Open | Unresolved | 24/Feb/16 7:27 PM | 26/Feb/16 12:03 PM
Task | OPENNCP-87 | Run security test session. | Jerome Subiger | Jerome Subiger | Critical | Open | Unresolved | 24/Feb/16 7:28 PM | 24/Feb/16 7:28 PM
Epic | OS-1 | STORK Configuration in the OpenNCP Portal | Marcelo Fonseca | Marcelo Fonseca | Major | To Do | Unresolved | 05/Jun/14 11:19 AM | 09/Jun/14 10:54 AM
Epic | OS-2 | Integration of STORK with OpenNCP Portal | Marcelo Fonseca | Marcelo Fonseca | Major | To Do | Unresolved | 05/Jun/14 11:24 AM | 24/Jun/14 10:02 AM
Story | OS-21 | [STORK-TEAM] Setup and Instantiate the OpenNCP in Austria for testing purposes | Thomas Fleischmann | Marcelo Fonseca | Major | In Progress | Unresolved | 09/Jun/14 4:27 PM | 25/Jun/14 12:04 PM | 13/Jun/14
Epic | OS-22 | This epic is about the testing of STORK integration with OpenNCP | Marcelo Fonseca | Marcelo Fonseca | Major | To Do | Unresolved | 11/Jun/14 1:24 PM | 11/Jun/14 3:34 PM
Story | OS-23 | [STORK-TEAM] User Acceptance Test | Florian Reimair | Marcelo Fonseca | Major | To Do | Unresolved | 11/Jun/14 1:25 PM | 25/Jun/14 12:04 PM | 20/Jun/14
Epic | OS-3 | Conversion of STORK Capabilities to epSOS | Marcelo Fonseca | Marcelo Fonseca | Major | To Do | Unresolved | 05/Jun/14 11:25 AM | 24/Jun/14 3:40 PM
Improvement | OS-35 | Adopt changes in openstork plugin related to “mandate” attributes in the stork response | Kostas Karkaletsis | Stéphane Spahni | Major | To Do | Unresolved | 28/Apr/15 11:24 AM | 28/Apr/15 11:26 AM
Improvement | OS-36 | Allow user to select the country of PEPS to be used from the portal in the PAC scenario | Kostas Karkaletsis | Kostas Karkaletsis | Major | To Do | Unresolved | 28/Apr/15 11:08 PM | 28/Apr/15 11:08 PM
Epic | OS-4 | This epic represents the setup of development environment, including repositories, mock software, etc. | Marcelo Fonseca | Marcelo Fonseca | Major | To Do | Unresolved | 05/Jun/14 3:25 PM | 11/Jun/14 4:14 PM
New Feature | PT-113 | XDR Consent Discard | Konstantin Hyppönen | Marcelo Fonseca | Trivial | Open | Unresolved | 2012-11-14 09:41 | 2013-03-20 17:56
New Feature | PT-114 | XDR - Dispensation Service - Discard() operation | Konstantin Hyppönen | Marcelo Fonseca | Major | Open | Unresolved | 2012-11-14 09:43 | 2013-01-14 14:11
Improvement | PT-115 | Multiple dispensations in single XDR message | Konstantin Hyppönen | Marcelo Fonseca | Trivial | Open | Unresolved | 2012-11-14 09:46 | 2013-03-20 17:59
Task | PT-117 | Invokation of call to Consent Mgr regarding create, discard and check | Marcelo Fonseca | Stefan Gustafsson | Trivial | Open | Unresolved | 2012-11-14 14:14 | 01/Aug/13 4:22 PM
Sub-task | PT-131 | PT-114 NCP-A implementation | Konstantin Hyppönen | Stefan Gustafsson | Major | Open | Unresolved | 10/Dec/12 10:46 AM | 13/Dec/12 9:06 PM
Sub-task | PT-132 | PT-114 NCP-B & Client Connector implementation | Marcelo Fonseca | Stefan Gustafsson | Major | Open | Unresolved | 10/Dec/12 10:46 AM | 10/Dec/12 10:47 AM
Epic | PT-174 | Patient Access to its own information in different languages | Konstantin Hyppönen | Licínio kustra Mano | Major | Open | Unresolved | 2013-01-30 17:16 | 27/Jun/14 11:32 PM
Epic | PT-175 | Health Care Encounter Report | Konstantin Hyppönen | Licínio kustra Mano | Major | Open | Unresolved | 2013-01-30 23:39 | 01/Aug/13 1:23 PM
Epic | PT-176 | Medication Related Overview | Konstantin Hyppönen | Licínio kustra Mano | Major | Open | Unresolved | 2013-01-30 23:39 | 2013-11-06 11:07
Story | PT-179 | Patient access requesting the translation of an eP | Licínio kustra Mano | Licínio kustra Mano | Trivial | Open | Unresolved | 2013-01-30 23:59 | 2014-03-14 11:21
Story | PT-180 | Patient access requesting for the most suitable PoC in a given country | Licínio kustra Mano | Licínio kustra Mano | Trivial | Open | Unresolved | 2013-01-31 | 30/Apr/13 1:41 PM
Improvement | PT-249 | Refactoring of PT-219 (Some exception classes need to be moved to another project and to different packages) | Konstantin Hyppönen | Mika Myllyvirta | Major | Open | Unresolved | 08/Apr/13 3:50 PM | 05/Feb/15 11:23 AM
Bug | PT-276 | Prefix urn:oid: must be added to OIDs | Konstantin Hyppönen | Konstantin Hyppönen | Minor | Open | Unresolved | 19/Apr/13 9:47 AM | 09/Feb/15 2:49 PM
Story | PT-295 | HCER Integration Tests | Marcelo Fonseca | Marcelo Fonseca | Minor | Open | Unresolved | 08/Jul/13 12:47 PM | 04/Feb/15 1:56 PM
Sub-task | PT-299 | PT-295 Extend integration tests for CLIENT part with LIVE form/portal POST | Marcelo Fonseca | Marcelo Fonseca | Minor | Open | Unresolved | 08/Jul/13 2:35 PM | 2013-10-10 17:30
Task | PT-30 | discard() operations for XDR Server (consent and eDispensation) | Stefan Gustafsson | Konstantin Hyppönen | Minor | Open | Unresolved | 29/Aug/12 9:33 AM | 2013-03-20 17:57
Improvement | PT-347 | Send CDA document transformation/translation errors to the portal. | Marcelo Fonseca | Licínio kustra Mano | Minor | Open | Unresolved | 2013-01-09 11:36 | 09/Feb/15 2:14 PM
Story | PT-348 | HCER Service for ePrescription Extension | Steen Manniche | Licínio kustra Mano | Trivial | Open | Unresolved | 2013-01-31 00:13 | 01/Aug/13 3:19 PM
Improvement | PT-37 | Assertion extraction code reuse in server and client part | Konstantin Hyppönen | Konstantin Hyppönen | Trivial | Open | Unresolved | 2012-09-05 20:47 | 2013-03-20 17:57
Story | PT-385 | Extended Security Safeguards IMPROVEMENTS | Licínio kustra Mano | Licínio kustra Mano | Major | Open | Unresolved | 2013-10-16 02:50 | 26/Feb/16 10:28 AM
Bug | PT-389 | Problem retrieving pdf document in MRO Scenario | Marcelo Fonseca | Kostas Karkaletsis | Major | Open | Unresolved | 2013-11-06 11:07 | 09/Feb/15 2:18 PM
Improvement | PT-391 | CI Environment <-> IHE Services: SAML Assertions | Marcelo Fonseca | Marcelo Fonseca | Minor | Open | Unresolved | 2013-11-19 09:29 | 09/Feb/15 2:20 PM
Improvement | PT-392 | [ Impedded ] Invoke validator for TRC Assertion | Marcelo Fonseca | Marcelo Fonseca | Minor | Open | Unresolved | 2013-11-19 09:30 | 24/Feb/16 4:28 PM
Improvement | PT-393 | [ Impedded ] Invoke validator for HCP Assertion | Marcelo Fonseca | Marcelo Fonseca | Minor | Open | Unresolved | 2013-11-19 09:30 | 09/Feb/15 2:21 PM
Task | PT-395 | [Nice to Have] Store report files in Jenkins Job and present links in console output | Marcelo Fonseca | Marcelo Fonseca | Major | Open | Unresolved | 2013-11-22 18:11 | 03/Dec/13 9:48 AM
Bug | PT-397 | XCA Query workflow messages are being validated twice in NCP-A+B | Marcelo Fonseca | Marcelo Fonseca | Major | Open | Unresolved | 2013-11-27 12:28 | 06/Apr/15 9:16 AM
Bug | PT-401 | Date and time weird format in validation report | Marcelo Fonseca | Gareth Woodham | Major | Open | Unresolved | 2013-11-28 11:15 | 2013-11-28 11:16
Improvement | PT-402 | Order of validation reports | Marcelo Fonseca | Gareth Woodham | Minor | Open | Unresolved | 2013-11-28 13:21 | 2013-11-28 13:25
Bug | PT-411 | Missing HCER property in ctx_tm.xml at XCA Client and Server Implementations | Stéphane Spahni | Marcelo Fonseca | Critical | Open | Unresolved | 2014-09-17 13:00 | 07/Jul/15 10:22 AM
Improvement | PT-44 | Patient Service: List() Operation request doesn't support $XDSDocumentEntryTypeCode parameter | Stefan Gustafsson | Marcelo Fonseca | Trivial | Open | Unresolved | 2012-09-10 10:24 | 2013-03-20 17:57
Improvement | PT-45 | Patient Service: List() Operation request doesn't support $XDSDocumentEntryFormatCode parameter | Stefan Gustafsson | Marcelo Fonseca | Minor | Open | Unresolved | 2012-09-10 10:26 | 2013-03-20 17:57
Improvement | PT-46 | Consent Service: Put() operation request doesn't support $XDSDocument.EntryUUID metadata element | Stefan Gustafsson | Marcelo Fonseca | Trivial | Open | Unresolved | 2012-09-10 10:55 | 2013-03-20 17:57
Improvement | PT-88 | Patient data fetch from national implementation can be optimized | Marcelo Fonseca | Mika Myllyvirta | Trivial | Open | Unresolved | 2012-10-12 08:23 | 01/Aug/13 4:22 PM
Improvement | SEC-1 | Assertion signature validation | Soeren Bittins | Konstantin Hyppönen | Critical | Open | Unresolved | 03/Dec/13 10:47 AM | 24/Feb/16 4:28 PM
Improvement | TM-12 | Activate test units with the last version of POSAM | Milada Kovarova | Arnaud Gaudinat | Minor | Open | Unresolved | 2012-10-18 15:36 | 2013-09-10 10:25
Bug | TM-55 | Transformation of coded element Author in ePrescription CDA level 1 produced by Sweden is not correct. | Oskar Thunman | Milada Kovarova | Major | Open | Unresolved | 2013-09-10 11:04 | 16/Jun/15 3:28 PM
Bug | TM-56 | Patient consent is not recognized | Stéphane Spahni | Stéphane Spahni | Major | Reopened | Unresolved | 2013-10-02 16:36 | 07/Jul/15 10:26 AM
Bug | TM-60 | Patient consent not recognized (4510: Unknown CDA Document code [57016-8]) | Arnaud Gaudinat | Stéphane Spahni | Major | Open | Unresolved | 22/Apr/15 2:02 PM | 22/Apr/15 5:42 PM
Bug | TSLED-10 | Cannot create TSL | João Cunha | Massimiliano Masi | Blocker | Open | Unresolved | 03/Dec/15 5:28 PM | 03/Dec/15 5:29 PM
Story | TSLED-4 | IMPLEMENT: TSL-EDITOR Refactor | Licínio kustra Mano | Rui Alves | Major | Open | Unresolved | 15/Jun/15 3:45 PM | 24/Feb/16 5:02 PM
Story | TSLED-5 | Technical Design: TSL-EDITOR Refactor | Licínio kustra Mano | Rui Alves | Major | Open | Unresolved | 15/Jun/15 3:56 PM | 24/Feb/16 5:02 PM
Bug | TSLED-9 | Unable to set the country code | João Cunha | Massimiliano Masi | Minor | Open | Unresolved | 03/Dec/15 3:11 PM | 03/Dec/15 3:12 PM
Story | TSLSYN-12 | IMPLEMENT: TSL-Sync Refactor | Licínio kustra Mano | Rui Alves | Major | Open | Unresolved | 15/Jun/15 3:44 PM | 24/Feb/16 5:02 PM
Story | TSLSYN-13 | Technical Design: TSL-Sync Refactor | Licínio kustra Mano | Rui Alves | Major | Open | Unresolved | 15/Jun/15 3:48 PM | 24/Feb/16 5:01 PM
Improvement | TSYNC-1 | Use the same conventions in all components | João Cunha | Stéphane Spahni | Major | Open | Unresolved | 2013-03-08 14:41 | 16/Jun/15 11:28 AM
Story | TSYNC-4 | TSAM-sync adaptation for CTS2 compliance | Arnaud Gaudinat | Licínio kustra Mano | Major | Open | Unresolved | 2013-01-31 12:09 | 2013-10-16 02:52
Sub-task | TSYNC-5 | TSYNC-4 Build CTS2 compliant REST client | Marcelo Fonseca | Marcelo Fonseca | Major | Open | Unresolved | 2013-10-15 09:32 | 17/Dec/13 1:31 PM
Sub-task | TSYNC-6 | TSYNC-4 Adjust DAOs to fill the database using the REST client | Marcelo Fonseca | Marcelo Fonseca | Major | Open | Unresolved | 2013-10-15 09:34 | 17/Dec/13 1:31 PM
Task | TSYNC-7 | Syncing terminologies, cannot retrieve from the central services. | Rui Alves | Rui Alves | Major | In Progress | Unresolved | 15/Jun/15 3:52 PM | 2015-09-30 13:57
Improvement | UT-10 | [PAT] Automated Testing Tool: Implement threading mechanism | Marcelo Fonseca | Marcelo Fonseca | Major | Open | Unresolved | 07/Apr/14 11:36 AM | 16/Jun/15 11:48 AM
Improvement | UT-11 | [PAT] Automated Testing Tool: Separate Messages From Reports | Marcelo Fonseca | Marcelo Fonseca | Major | Open | Unresolved | 07/Apr/14 3:10 PM | 16/Jun/15 2:43 PM
Improvement | UT-12 | [PAT] Automated Testing Tool: Capture Assertions also and set them without validation report | Marcelo Fonseca | Marcelo Fonseca | Minor | Open | Unresolved | 08/Apr/14 11:30 AM | 26/Feb/16 10:30 AM
Task | UTIL-8 | Decision on whether to remove unused class DBConnection, XPathEvaluator from the utils codebase | Marcelo Fonseca | Steen Manniche | Minor | Open | Unresolved | 2013-01-11 14:32 | 01/Aug/13 4:22 PM
Generated at Wed Mar 02 18:54:59 CET 2016 by Jerome Subiger using JIRA 7.2.0-OD-03-010#72000-sha1:d4f0e55382250d79af2a76d8b0ff23d12af94da2.